## Slide 1: Subrecipient Monitoring

## Slide 2: AGENDA
Roles & Responsibilities
Guidance & Resources

## Slide 3: Roles & Responsibilities

## Slide 4: OGC & Fiscal Compliance
OGC Subcontracts:
  The primary office within OGC responsible for outgoing subagreements.
  OGC Subcontracts handles the initial compliance review, drafts and negotiates subagreements, executes subagreements, completes risk assessment (Federal/Federal flow-through) and amends any subrecipient agreements.
OGC Pre-Award: Reviews proposals during the routing process to ensure the subrecipient budget and indirect cost rate conforms to sponsor requirements.
OGC Post-Award: Submits financial reports to sponsors containing financial information from the University’s subrecipients and reviews and approves Marketplace submissions related to subagreements.
Fiscal Compliance: Reviews the University’s subrecipients’ single audits and issues management decisions for audit findings. Regularly keeps track of current audit environment.

## Slide 5: PI & Department Administration
Administrative units assist PIs in requesting subagreements, reviewing and approving invoices, ensuring deliverables are received on time, providing guidance on addressing subrecipient non-compliance, and documenting monitoring activities.
Roles & Responsibilities are covered in Chapter 6.3 of the Sponsored Project Handbook
The PI, or their delegate, is responsible for ensuring that each subrecipient is
  making adequate progress on the subagreement
  complies with the financial and administrative requirements.
The PI must maintain regular communication with the subrecipient and ensure an informal progress update at least quarterly. This update can be in the form of an email, phone call, video conference, or other meeting. Monitoring activities must be documented.

## Slide 6: PI & Department Administration
Minimum Subrecipient Monitoring Requirements:
  Create a monitoring plan that follows policy/guidance
  Consistently execute that monitoring plan
  Document monitoring activities in a way that aligns with plan and can be verified by internal or external auditors

## Slide 7: Guidance & resources

## Slide 8: Sponsored Project handbook
Sponsored Project Handbook
Chapter 6 covers all topics related to Subagreements.
  Section 6.3 – Describes Roles and Responsibilities
  Section 6.7 – Subrecipient Monitoring Plans and Monitoring Records
PIs and administrative units should develop and comply with a subrecipient monitoring plan for each subagreement.
For most low-risk subrecipients, a standard monitoring plan may be adopted.
For medium/high-risk subrecipients, a tailored monitoring plan should specifically address identified risks from the risk assessment.
Initial email from the Contracts team will state your subrecipients risk level.

## Slide 9: Additional resources
OGC Subcontract Monitoring Record - Can be used by departments and schools to document subrecipient monitoring efforts and maintain an audit trail. Use of the tracking record is encouraged at all risk levels but especially for medium and high risk subrecipients.
Subcontract Management Document – Describes best practices and processes for Subcontracts Management. Includes suggestions for medium/high risk subrecipients.
Subcontract Monitoring Invoice Checklist - A guide for reviewing subrecipient invoices.
All resources can be found in the A-Z Index, under ‘S’

## Slide 10: Common audit observations with subrecipients
Equipment purchases - Subrecipients fail to follow their internal procurement policies and/or suspension and debarment requirement checks.
Monitoring third-tier subrecipients.
Property management – only necessary for non-exempt property (likely not research awards).
Travel – Subrecipients fail to follow internal travel policies. For international subrecipients, must comply with applicable Fly America requirements.

## Slide 11: Email Update & training
Upcoming Training
CU: SP: Subrecipient Monitoring
Registration Link
November 17 & 18, 2025
12:00p - 1:00p
Instructor: Shane Jernigan
Email Update
The standard email that is sent to all PI/Admin Delegates at the start of a new subagreement has been updated to include more guidance related to subrecipient monitoring and includes numerous links discussed today.
This provides you with another easy to click resource to help guide your monitoring plan and process.

## Slide 12: Thank you